## Sheet1
Issue Name | Module(s) Associated with Issue | Issue Description | Resolution | Status | Priority | Resource | Temporary Solution
Hold Time | IBM Watson | Currently, I have used randomly generated wait times between different dialogues - however, this information needs to come to us in a real world scenario with actual values - because I cant accurately predict this without real values. | Ask Telephony Team from now on to put in some extra effort and get us the start and end time per dialogue. | Pending | Low | Ramsha
Conversation Gaps | IBM Watson | I've looked at the transcriptions of several calls from IBM Watson - and in almost all of them - if a speaker takes a pause while talking and the other one says nothing at all - even if that pause is 2 or more minutes long - IBM doesnot detect this gap - and carries out a single dialogue with no indication of delay between words whatsoever. | Tinker with IBM Watson API settings or talk to a representative. | Pending | Low | Ramsha
Interruption | IBM Watson | I've looked at alot of transcriptions for this - and IBM Watson doesnt detect interruption - instead it adds all words in the same dialogue spoken by all speakers - as if it came from the main speaker of the dialogue. for example, muffled acknowledgments like: uh-huh, mm-hmm, etc. | Tinker with IBM Watson API settings or talk to a representative. | Pending | Low | Ramsha
Spacy Tags Lag | Feature Engineering Tags | As we add more and more data, the time taken by spacy library to process tags keeps increasing. As of now, it takes 6 minutes 40 secs to process 80 class (3657 sentences) - which hinders our performance speed if we use a singular service to run code over and over again. | Use NLTK instead (Already tried - almost takes equivalent time - also doesnt have options for two tags: coref and dep. Need to look at some other libraries for every tag. | Pending | Low | Ramsha
Test QA KPI Data | Active Listening | I've looked at several calls with inactive listening - and the problem is, the CSR is giving acknowledgment statements, so I can't dedeuct marks in those scenarios. Same goes for inattentiveness - the query doesnt get transcribed properly and I cant track it further in the conversation. | Select a few calls to get tested by QA again - and get their help in marking areas where we shud deduct marks. | Pending | Medium | Ramsha
Model Configs | Vectorization | For Feature Engineering and PreProcessing, I have previously defined configurations that say: this is the data i require to function, else i wont. But this is not the case for vectorization. For vectorization, i dont need data in any particular type - it all depends on the model thats using a vectorizer for its use - and so the configs need to come from that end. | For every nlp_model_version_id, we need to store a flag that says: vectorizer_type: tfidf, count, onehot, etc. Then all I'll have to do is read the features a model needs and vectorize them on the basis of vectorizer_type for the given model. | Pending | High | Ramsha | We are going to keep a flag inside nlp_model_1s table that defines a vectorizer type for every model.
Audio Graphs | Appropriate Tone | Even if we dont have access to audio files for calls, its possible to get access to the audio graphs - that give values for pitch, frequency, noise and other factors inside every call - might even help us out with speaker diarization, if its not possible to attain it from Batch Team. | Discuss this with Batch Team while their configuring the system for retrieving calls and their transcripts | Pending | Medium | Ramsha
Separated Calls | Speaker Diarization | If we can get separated calls for every speaker on call from IVR - it will be easier for us to keep track of who's talking and help improve model performance (like make it actually functioning - instead of us deducting marks of a CSR for the customer's fault) | Discuss this with Batch Team while their configuring the system for retrieving calls and their transcripts | Pending | Medium | Ramsha
KPI Classes | Model Output | For some KPIs, such as Appropriate Empathy – the model will give dialogue-wise outputs, and so we will need to implement some coding logic to convert that output to a conversation KPI answer. Which means that simply using configurations is not enough. | Discuss with Ali Shan about this issue in order to decide whether we can come up with configs that can deal with aggregate solutions or do we need to write classes. | Pending | High | Ramsha | We will adjust in Configurations.
Libraries List | Project Testing | Need to maintain a list of libraries used and their versions for the project – so that new resources can install them instantly. | Just need to start work on this myself. | Pending | Low | Ramsha